## Formato descripción HU
HU Framework Matrix
ITEM | PROBLEM | WHAT (REQUEST) | WHAT FOR (SOLUTION) | FOR WHO (USUARIO) | HOW (DESCRIPTION OF TASKS) | MADE BY (PROG. RESP.) | HOW LONG (HOURS) | DATE OF DELIVERY | PRIORITY | STATUS | TEST (HOW TO VERIFY) | COMENTARIES | HISTORY NAME
REQ001 | Opcions menu | Log in | So you can schedule, postpone or cancel appointments | Customer (owner) | In the main interface a menu will be displayed where it will be indicated that you must log in to make any changes in the system, if there are no changes you can view the calendar in another option of the main menu | Steven Pozo | In process | August | hight | In process | At the time of entering your previously created username and password, you can enter to make any changes in the system | The username and password must be alphanumeric. | Validate data
REQ002 | Schedule appointments | Save customer data | To be able to schedule a day with your appointment | Customer (owner) | The owner must enter the name, surname, ID number and email of the client that will be requested. | Erick Moreira | In process | August | hight | In process | Once the data is saved, the appointment already scheduled can be viewed later in a section. | The data entered must be correct | Data entry
REQ003 | Generate service billing | Show the amount to be charged for the service provided | So that there is proof of the service provided and a backup of it | Customer (owner) | Once the appointment is scheduled, you can pay for it or you can pay in installments, whatever the method, at the beginning of this you must invoice the amount that the service that will be provided acquires. | Elkin Pabón - Diego Ponce | In process | August | hight | In process | Everything will be verified once the payment invoice is issued | The data entered must be correct | invoice issuance

## Historia de Usuario
HISTORIA DE USUARIO (HU)
| ITEM |  | USUARIO |  | STATUS
| REQ001 |  | Customer (owner) |  | In process
| TIEMPO |  | PRIORIDAD |  | PROG. RESP
| In process |  | hight |  | Steven Pozo
| QUE | Log in |  | PARA QUE | So you can schedule, postpone or cancel appointments |  | COMO | In the main interface a menu will be displayed where it will be indicated that you must log in to make any changes in the system, if there are no changes you can view the calendar in another option of the main menu
| NOMBRE HISTORIA |  | Validate data
| PRUEBA |  | At the time of entering your previously created username and password, you can enter to make any changes in the system |  |  | COMENTARIOS | The username and password must be alphanumeric.